## Slide 1
Plan
Test
Develop
Reflexion
15/Juni
16/Jun
17/Jun
20/Jun
21/Jun
22/Jun
23/Jun
24/Jun
27/Jun
28/Jun
29/Jun
30/Jun
2019
Planning nested Sprint
Subcontractor Selection
Integration I
Integration II
Integration III & IV
Prototype Development Phase I
Development Phase II
Pitch
Project roadmap
Vorstellung gespräch
Working Plans
Planning micro Sprint 1
Planning micro Sprint 2
Planning micro Sprint 3
Planning micro Sprint 4
Reflexion micro Sprint 1
Reflexion micro Sprint 2
Reflexion micro Sprint 3
Reflexion micro Sprint 4
Reflexion gespräch
Dokumentation